# Document 9 — POS Appliance Platform Implementation Master Plan

## Document Control

Project Name: POS Appliance Platform
Internal Codename: CounterOS / POS Appliance Core
Primary Initial Vertical: Hospital POS
Document Type: Implementation Master Plan
Document Version: 1.0 Final Draft
Status: Execution Planning Baseline
Depends On:

- Document 1 — POS Appliance Platform Architecture Document v1.0 Final Locked

- Document 2 — POS Appliance Platform Requirements Document v1.0 Final Locked

- Document 3 — POS Appliance Platform Database Schema Document v1.0 Final Draft

- Document 4 — POS Appliance Platform API Contract Document v1.0 Final Draft

- Document 5 — POS Appliance Platform Screen Map Document v1.0 Final Draft

- Document 6 — POS Appliance Platform Sync Engine Document v1.0 Final Draft

- Document 7 — POS Appliance Platform Recovery Engine Document v1.0 Final Draft

- Document 8 — POS Appliance Platform Development Rules and Definition of Done Document v1.0 Final Draft

Purpose: Define the exact implementation order, phase boundaries, task sequencing, build rules, acceptance gates, testing gates, and Codex/developer execution discipline for building the offline-first POS Appliance Platform without broken screens, fake buttons, placeholder APIs, frontend/backend mismatch, or unfinished production flows.

# 1. Executive Summary

This document defines how the POS Appliance Platform must be built.

The previous documents define what the system is.
This document defines how to execute the build.

The implementation must follow a strict phase-by-phase approach:

txt id="rp5k3c" Foundation first Database second Backend APIs third Frontend shell fourth One complete billing flow fifth Recovery sixth Sync seventh Reports/support eighth Hardening last

The project must not begin with fancy dashboards, visual polish, or extra modules.

The first real success milestone is:

txt id="120evq" Login → Open cashier session → Create draft bill → Add service → Finalize cash bill → Generate receipt → Print/reprint → Queue sync event → Recover after restart

The most important implementation rule is:

Do not build more screens before one complete local-first billing flow works end-to-end.

# 2. Implementation Principles

## 2.1 Build Durable Core Before UI Polish

The platform must prioritize:

txt id="09skeb" Local database safety Backend business correctness API contract accuracy Recovery behavior Sync event correctness Frontend state correctness

Only after these work should UI polish expand.

## 2.2 Backend and Database Before Frontend Complexity

Frontend screens must not be created without real backend APIs.

Correct build sequence:

txt id="jl1qia" Database migration → Backend model/repository/service → API endpoint → API test → Frontend API client → Frontend screen → Frontend states → Integration test

Wrong build sequence:

txt id="6hmoj9" Pretty screen → Fake data → Fake button → Later backend guesswork

## 2.3 No Parallel Chaos

Do not build many modules at the same time.

Allowed early focus:

txt id="yt635n" Auth Device Session Catalog Patient Draft billing Cash finalization Receipt Printer job Sync outbox Recovery

Not allowed early:

txt id="fjy2sb" Advanced IP billing Insurance billing Full pharmacy stock AI reports Complex analytics Multi-branch dashboards Fancy admin SaaS panel Payment gateway settlement

## 2.4 Every Phase Must Have an Exit Gate

A phase is complete only when:

txt id="r3x45r" Code is implemented API works Database migration works Frontend route works if applicable Tests pass No fake buttons exist No broken routes exist No known P0 issue remains

Do not move to the next phase just because files were created.

# 3. Recommended Technology Stack for MVP

## 3.1 Backend

txt id="70qt08" Python FastAPI SQLAlchemy Alembic Pydantic Pytest SQLite for terminal database

## 3.2 Frontend

txt id="9mp8gl" React / Next.js TypeScript TanStack Query Zustand only where needed Tailwind CSS Central API client

## 3.3 Runtime

txt id="b60lai" Linux-compatible local development first systemd service files later Chromium kiosk or Electron shell later

## 3.4 Database

txt id="16e2kc" SQLite with WAL for terminal MVP PostgreSQL later for branch/cloud

# 4. Repository Creation Plan

## 4.1 Required Repository Structure

```txt id=“6359dh” pos-platform/ docs/ 01-architecture.md 02-requirements.md 03-database-schema.md 04-api-contract.md 05-screen-map.md 06-sync-engine.md 07-recovery-engine.md 08-development-rules-dod.md 09-implementation-master-plan.md

backend/ app/ main.py config.py startup.py shutdown.py

core/
    errors.py
    responses.py
    logging.py
    security.py
    permissions.py
    ids.py
    time.py
    idempotency.py

  database/
    connection.py
    migrations/
    models/
    repositories/
    transactions.py

  auth/
  users/
  roles/
  devices/
  licensing/
  sessions/
  patients/
  catalog/
  billing/
  payments/
  receipts/
  printer/
  sync/
  recovery/
  audit/
  reports/
  health/
  settings/
  support/
  backup/
  restore/
  updates/

  tests/

frontend/ app/ startup/ login/ dashboard/ session/ billing/ sync/ recovery/ reports/ settings/ hardware/ support/ audit/

components/
features/
lib/
  api/
  auth/
  permissions/
  idempotency/
  errors/
  formatting/
tests/

shared/ enums/ api-types/ constants/

os/ systemd/ kiosk/ install/ update/

scripts/ dev/ test/ build/ install/

---

# 5. Environment Plan

## 5.1 Required Environments

```txt id="qwxu1l"
development
staging
demo
production

## 5.2 Environment Rules

Development may use:

txt id="fh53ae" local SQLite mock printer adapter local dev server fake cloud sync server for testing seed data

Production must not use:

txt id="emlv7r" fake login fake billing success fake printer success mock payment success hardcoded admin user hardcoded test catalog placeholder APIs

## 5.3 Required Environment Variables

Backend:

txt id="tueitc" APP_ENV APP_NAME API_VERSION DATABASE_URL LOCAL_DEVICE_ID LOG_LEVEL ENABLE_MOCK_PRINTER ENABLE_FAKE_SYNC_SERVER SYNC_SERVER_URL BACKUP_PATH

Frontend:

txt id="o3zzj2" NEXT_PUBLIC_APP_ENV NEXT_PUBLIC_LOCAL_API_BASE_URL NEXT_PUBLIC_APP_NAME

Production environment must clearly show environment name in settings/support.

# 6. Phase 0 — Project Foundation

## 6.1 Goal

Create the base repository, backend skeleton, frontend skeleton, shared constants, environment config, and standard API response system.

No billing logic yet.

## 6.2 Documents Used

txt id="1avkdh" Document 1 — Architecture Document 4 — API Contract Document 5 — Screen Map Document 8 — Development Rules

## 6.3 Backend Tasks

txt id="er5xe7" Create FastAPI app. Create config loader. Create standard success response helper. Create standard error response helper. Create request ID middleware. Create logging setup. Create health router. Create startup router. Create version endpoint. Create app exception handler. Create environment detection.

## 6.4 Frontend Tasks

txt id="2kaqip" Create Next.js/React app. Create central API client. Create standard API response parser. Create standard error parser. Create app shell layout. Create startup route. Create API unavailable screen. Create support-required screen. Create permission-denied screen.

## 6.5 Shared Tasks

txt id="kqg0q4" Create enum constants. Create permission constants. Create route constants. Create API path constants. Create error code constants.

## 6.6 Must Not Build Yet

txt id="o53lkr" No billing screen. No fake dashboard stats. No fake login. No fake patient data. No placeholder buttons. No dummy sync counters.

## 6.7 Required APIs

txt id="rqm9n3" GET /api/v1/health GET /api/v1/health/version GET /api/v1/startup/status

## 6.8 Exit Gate

Phase 0 is complete only when:

txt id="zl2d7i" Backend starts successfully. Frontend starts successfully. Frontend can call local health API. Startup screen shows real health/version response. API unavailable screen works if backend is stopped. Standard response format is used. Standard error format is used. Request ID appears in responses. No placeholder production buttons exist.

# 7. Phase 1 — Database Foundation

## 7.1 Goal

Create the local database foundation with migrations, WAL mode, common tables, runtime state, and migration tracking.

## 7.2 Documents Used

txt id="f3372s" Document 3 — Database Schema Document 7 — Recovery Engine Document 8 — Development Rules

## 7.3 Backend Tasks

txt id="s9umnr" Add SQLAlchemy database connection. Add Alembic migrations. Enable SQLite WAL mode. Enable foreign keys. Add database health check. Add migration_records table. Add app_runtime_state table. Add audit_logs table. Add organizations table. Add branches table. Add devices table. Add settings table. Add basic seed data for development only.

## 7.4 Required Tables

txt id="2g08dt" organizations branches devices settings migration_records app_runtime_state audit_logs

## 7.5 Required APIs

txt id="0bdgj7" GET /api/v1/health/database GET /api/v1/health/version GET /api/v1/device/status

## 7.6 Required Tests

txt id="4fvki7" Fresh DB migration test. Existing DB migration test. Foreign keys enabled test. WAL mode enabled test. Database health success test. Database health failure test. Migration failure blocks startup test.

## 7.7 Exit Gate

Phase 1 is complete only when:

txt id="cchzds" Fresh database can be created from migrations. Database health endpoint works. Startup detects DB availability. Migration version is visible. Runtime state can be written. Audit log can be inserted. No manual DB creation is required.

# 8. Phase 2 — Auth, Device, Permissions, and Sessions

## 8.1 Goal

Implement user login, offline-capable cached auth foundation, role permissions, device identity, and cashier sessions.

## 8.2 Documents Used

txt id="etw9de" Document 2 — Requirements Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map

## 8.3 Backend Tasks

txt id="lqf1hh" Create users table/model/repository. Create roles table/model/repository. Create permissions table/model/repository. Create role_permissions table. Create user_roles table. Create login_sessions table. Create cashier_sessions table. Implement login. Implement offline login policy foundation. Implement auth/me. Implement logout. Implement permission checker. Implement session open. Implement session current. Implement session close. Create audit logs for auth/session actions. Create sync events for session open/close if sync foundation exists, or prepare hook.

## 8.4 Frontend Tasks

txt id="cv7i84" Create login screen. Create offline login behavior. Create dashboard shell. Create open session screen. Create close session screen. Create permission guard. Show current user/session in top bar.

## 8.5 Required APIs

txt id="esyxqp" POST /api/v1/auth/login POST /api/v1/auth/offline-login GET  /api/v1/auth/me POST /api/v1/auth/logout GET  /api/v1/sessions/current POST /api/v1/sessions/open POST /api/v1/sessions/close GET  /api/v1/device/status

## 8.6 Required Screens

txt id="d1hb3k" /login /dashboard /session/open /session/close /permission-denied

## 8.7 Required Tests

txt id="zq4k46" Login success. Login invalid credentials. Offline login allowed for cached user. Offline login blocked for uncached user. Permission denied test. Open session success. Open session duplicate blocked. Close session success. Close session without session blocked.

## 8.8 Exit Gate

Phase 2 is complete only when:

txt id="53xpjz" User can login. User can logout. Current user API works. Permission guard works. Cashier can open session. Dashboard shows active session. Cashier can close session. Session survives backend restart. No billing can finalize without active session later.

# 9. Phase 3 — Master Data, Patient, and Catalog Foundation

## 9.1 Goal

Implement the local cached hospital master data needed for billing.

## 9.2 Documents Used

txt id="v009jw" Document 2 — Requirements Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map

## 9.3 Backend Tasks

txt id="ycguk0" Create patients model/repository/service. Create departments model/repository/service. Create doctors model/repository/service. Create services model/repository/service. Create price_lists/service_prices model/repository/service. Create tax_rules foundation if needed. Implement patient search. Implement patient create. Implement service search. Implement department list. Implement doctor list. Ensure price/catalog version fields exist.

## 9.4 Frontend Tasks

txt id="lr5qfj" Add patient search component. Add patient create form. Add service search component. Add department selector. Add doctor selector. Handle empty catalog state. Handle offline cached data state.

## 9.5 Required APIs

txt id="l0mog3" GET  /api/v1/patients POST /api/v1/patients GET  /api/v1/catalog/services GET  /api/v1/catalog/departments GET  /api/v1/catalog/doctors

## 9.6 Required Tables

txt id="yjqu2g" patients departments doctors services price_lists service_prices tax_rules master_sync_state

## 9.7 Required Tests

txt id="kb96cj" Patient search works. Patient create works. Service search works. Department list works. Doctor list works. Inactive service not selectable. Service returns catalog_version. Service returns price_version.

## 9.8 Exit Gate

Phase 3 is complete only when:

txt id="a2g0d1" Patient can be searched locally. Patient can be created locally. Services can be searched locally. Catalog data includes price snapshots. Frontend can select patient/service without fake data. Empty catalog state is handled.

# 10. Phase 4 — Draft Billing and Autosave

## 10.1 Goal

Implement draft bill creation and autosave, including draft items and backend-calculated totals.

## 10.2 Documents Used

txt id="eijqgh" Document 2 — Requirements Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map Document 7 — Recovery Engine

## 10.3 Backend Tasks

txt id="0y2gbu" Create bill_drafts model/repository/service. Create bill_draft_items model/repository/service. Implement draft number generation. Implement create draft. Implement get draft. Implement list drafts. Implement update draft header. Implement add draft item. Implement edit draft item. Implement remove draft item. Implement backend total calculation. Implement autosave timestamp update. Implement audit logs for draft actions where required. Prepare recovery detection for open drafts.

## 10.4 Frontend Tasks

txt id="8506mh" Create /billing/new screen. Create /billing/drafts screen. Create /billing/drafts/:draftId workspace. Wire patient selection. Wire service search. Wire add item. Wire edit quantity/discount. Wire remove item. Show totals from backend. Show autosave indicator. Show empty item state. Disable finalize if no items.

## 10.5 Required APIs

txt id="3g101m" POST   /api/v1/bills/drafts GET    /api/v1/bills/drafts GET    /api/v1/bills/drafts/{draft_id} PATCH  /api/v1/bills/drafts/{draft_id} POST   /api/v1/bills/drafts/{draft_id}/items PATCH  /api/v1/bills/drafts/{draft_id}/items/{item_id} DELETE /api/v1/bills/drafts/{draft_id}/items/{item_id}

## 10.6 Required Tests

txt id="fmz0gq" Create draft with active session. Create draft without session blocked. Draft survives frontend refresh. Draft survives backend restart. Add item updates totals. Edit item updates totals. Remove item updates totals. Finalized draft cannot be edited later. Empty draft state works.

## 10.7 Exit Gate

Phase 4 is complete only when:

txt id="dmj3al" Draft bill can be created locally. Draft changes are autosaved. Draft items preserve price/catalog version. Totals are calculated by backend. Frontend displays backend totals. Draft survives refresh/restart. No fake billing data exists.

# 11. Phase 5 — Bill Finalization, Cash Payment, Receipt Creation, and Outbox Event

## 11.1 Goal

Complete the first real financial flow: draft bill becomes finalized bill with cash payment, receipt, audit log, and sync event.

## 11.2 Documents Used

txt id="p0hinm" Document 2 — Requirements Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map Document 6 — Sync Engine Document 8 — Development Rules

## 11.3 Backend Tasks

txt id="pdmq81" Create bills model/repository/service. Create bill_items model/repository/service. Create payments model/repository/service. Create receipts model/repository/service. Create sync_events model/repository/service. Implement bill number generation. Implement payment number generation. Implement receipt number generation. Implement idempotency service. Implement finalize draft transaction. Create final bill. Copy draft items into immutable bill_items snapshots. Create cash payment. Create receipt record. Create sync event. Create audit log. Mark draft finalized. Prevent duplicate finalization.

## 11.4 Frontend Tasks

txt id="pk20mm" Add Finalize Cash Bill action. Generate stable idempotency key. Disable finalize while processing. Show finalization error states. Route to receipt screen on success. Create bill detail screen. Create bills list screen.

## 11.5 Required APIs

txt id="u421yw" POST /api/v1/bills/drafts/{draft_id}/finalize GET  /api/v1/bills GET  /api/v1/bills/{bill_id} GET  /api/v1/payments/{payment_id} GET  /api/v1/receipts/by-bill/{bill_id}

## 11.6 Required Transaction

Finalization transaction must include:

txt id="me2mp3" Validate active session. Validate draft exists. Validate draft has items. Validate payment amount. Create bill. Create bill_items. Create payment. Create receipt. Create sync_event. Create audit_log. Update draft finalized state. Commit.

## 11.7 Required Tests

txt id="6de0mj" Finalize valid cash bill. Finalize empty draft blocked. Finalize without session blocked. Finalize same draft twice returns original/idempotent result. Double-click finalize creates one bill. Bill item snapshots preserve price. Payment created. Receipt created. Sync event created. Audit log created. Crash before commit creates no partial final bill. Crash after commit recovers finalized bill.

## 11.8 Exit Gate

Phase 5 is complete only when:

txt id="jo70b5" Cash bill finalizes offline. Bill/payment/receipt/sync/audit are created. Duplicate finalization is prevented. Final bill survives restart. Receipt record exists after finalization. Bill list/detail screens show real data.

# 12. Phase 6 — Receipt Printing and Printer Jobs

## 12.1 Goal

Implement printer job creation, print attempts, print retry, and reprint flow.

## 12.2 Documents Used

txt id="j57mfp" Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map Document 7 — Recovery Engine

## 12.3 Backend Tasks

txt id="k9a8rh" Create printer_jobs model/repository/service. Create printer adapter interface. Create mock printer adapter for dev. Implement printer status API. Implement print receipt API. Implement reprint receipt API. Implement retry printer job API. Update receipt print states. Track reprint count. Audit print/reprint actions.

## 12.4 Frontend Tasks

txt id="8n9b04" Create receipt screen. Create receipt preview. Add Print button. Add Reprint button. Show printer status. Show print job status. Create hardware/printer screen. Add retry failed job action.

## 12.5 Required APIs

txt id="1h32ww" POST /api/v1/receipts/{bill_id}/generate GET  /api/v1/receipts/{receipt_id} GET  /api/v1/receipts/by-bill/{bill_id} POST /api/v1/receipts/{receipt_id}/print POST /api/v1/receipts/{receipt_id}/reprint GET  /api/v1/printer/status POST /api/v1/printer/test GET  /api/v1/printer/jobs POST /api/v1/printer/jobs/{job_id}/retry

## 12.6 Required Tests

txt id="rg6msf" Print creates printer job before attempting print. Printer unavailable marks job failed. Retry failed job works. Pending print survives restart. Reprint increments reprint count. Reprint creates audit log. Printer failure does not undo bill.

## 12.7 Exit Gate

Phase 6 is complete only when:

txt id="phtxyc" Receipt can be viewed. Print job is created. Print success/failure is stored. Failed print can be retried. Reprint works with audit. Printer screen shows real job data.

# 13. Phase 7 — Recovery Engine Implementation

## 13.1 Goal

Implement startup recovery scan and recovery UI for active sessions, open drafts, unsynced bills, pending prints, unknown payments, and stale sync events.

## 13.2 Documents Used

txt id="mtphfd" Document 7 — Recovery Engine Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map

## 13.3 Backend Tasks

txt id="xr4nb9" Implement app_runtime_state updates. Detect unclean shutdown. Create recovery_markers. Detect open drafts. Detect active sessions. Detect unsynced bills. Detect pending/failed printer jobs. Detect unknown payments. Detect stale syncing events. Implement recovery/status API. Implement recovery/work-items API. Implement recovery/resolve API. Audit recovery actions.

## 13.4 Frontend Tasks

txt id="j7i62k" Create /recovery screen. Show active sessions. Show open drafts. Show unsynced bills. Show pending print jobs. Show unknown payments. Add Continue Session action. Add Open Draft action. Add Retry Print action. Add Resolve Marker action. Show recovery banner on dashboard.

## 13.5 Required APIs

txt id="laeg4b" GET  /api/v1/recovery/status GET  /api/v1/recovery/work-items POST /api/v1/recovery/resolve

## 13.6 Required Tests

txt id="9oqn9h" Unclean shutdown detected. Open draft recovered. Active session recovered. Unsynced bill shown. Pending print job shown. Unknown payment shown. Stale syncing event reset. Recovery marker resolved. Recovery action audited.

## 13.7 Exit Gate

Phase 7 is complete only when:

txt id="9ezds7" Recovery screen shows real recoverable work. Draft/session/bill/print recovery works. Startup routes to recovery when needed. No recovery data is deleted automatically. Recovery actions are audited.

# 14. Phase 8 — Sync Engine Implementation

## 14.1 Goal

Implement real local outbox sync engine behavior, retry, status APIs, event list, and master sync status foundation.

## 14.2 Documents Used

txt id="rmzf5d" Document 6 — Sync Engine Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map

## 14.3 Backend Tasks

txt id="2tx1mn" Implement sync_events repository/service. Implement sync event creation hooks. Implement sync scheduler. Implement event poller. Implement retry backoff. Implement stale syncing recovery. Implement sync status API. Implement sync events list/detail APIs. Implement manual retry APIs. Implement master_sync_state. Implement fake cloud sync server for development if needed.

## 14.4 Frontend Tasks

txt id="dksltt" Create /sync screen. Show pending count. Show failed count. Show conflict count. Show master sync status. Show event list. Add Retry All. Add Retry Event. Show sync status in top bar/dashboard.

## 14.5 Required APIs

txt id="l1m9c8" GET  /api/v1/sync/status GET  /api/v1/sync/events GET  /api/v1/sync/events/{event_id} POST /api/v1/sync/retry POST /api/v1/sync/events/{event_id}/retry GET  /api/v1/sync/master/status POST /api/v1/sync/master/refresh

## 14.6 Required Tests

txt id="s214i4" Pending events listed. Retryable failure schedules backoff. Manual retry resets event. Successful sync marks event synced. Duplicate accepted handled. Conflict creates sync_conflicts record. Sync events survive restart. Billing continues when sync fails.

## 14.7 Exit Gate

Phase 8 is complete only when:

txt id="fpii30" Sync status screen shows real DB counts. Sync events retry safely. Manual retry works. Outbox survives restart. Duplicate sync does not duplicate records. Frontend never calls cloud sync directly.

# 15. Phase 9 — Reports, Settings, Health, and Support

## 15.1 Goal

Implement local reports, settings, support diagnostics, backup status, and operational health visibility.

## 15.2 Documents Used

txt id="11dgra" Document 2 — Requirements Document 3 — Database Schema Document 4 — API Contract Document 5 — Screen Map Document 8 — Development Rules

## 15.3 Backend Tasks

txt id="ewx964" Implement today collection report. Implement cashier session report. Implement pending sync report. Implement department collection report if ready. Implement settings API. Implement support status API. Implement backup status API. Implement backup create API foundation. Implement audit logs view API.

## 15.4 Frontend Tasks

txt id="60br1i" Create reports screen. Create settings screen. Create support screen. Create audit screen if included. Show health status. Show version info. Show backup status. Show support actions.

## 15.5 Required APIs

txt id="g1wds8" GET /api/v1/reports/today-collection GET /api/v1/reports/cashier-session/{session_id} GET /api/v1/reports/pending-sync GET /api/v1/reports/department-collection GET /api/v1/settings PATCH /api/v1/settings GET /api/v1/support/status GET /api/v1/backups/status POST /api/v1/backups/create GET /api/v1/audit/logs

## 15.6 Required Tests

txt id="yf6iyw" Today collection uses local bills/payments. Cashier session report matches session totals. Pending sync report matches sync_events. Settings read works. Settings edit permission enforced. Support status works. Backup status works. Audit logs list works.

## 15.7 Exit Gate

Phase 9 is complete only when:

txt id="ci5fvc" Reports show real local data. Settings show real device/app info. Support screen shows real health. Backup status is visible. No report uses fake numbers.

# 16. Phase 10 — OS/Kiosk Packaging Foundation

## 16.1 Goal

Prepare the app to run like a Linux POS appliance.

## 16.2 Documents Used

txt id="v7a4gh" Document 1 — Architecture Document 8 — Development Rules

## 16.3 Tasks

txt id="bkuoeq" Create systemd service file for backend. Create systemd service file for sync service. Create systemd service file for hardware service if separate. Create kiosk launch script. Create local install script. Create local update placeholder mechanism without risky OTA. Create log directory setup. Create data directory setup. Create backup directory setup.

## 16.4 Required Service Files

txt id="wlpj3m" pos-api.service pos-sync.service pos-hardware.service pos-kiosk.service pos-health.service

## 16.5 Exit Gate

Phase 10 is complete only when:

txt id="b0whu8" Backend can start as service. Sync can start as service. Kiosk can launch frontend. Services restart on crash. Logs are written to expected location. Data paths are stable.

# 17. Phase 11 — MVP Hardening and Acceptance Testing

## 17.1 Goal

Run all MVP acceptance tests and fix P0 issues.

## 17.2 Required Test Categories

txt id="ol2t7f" Backend API tests Database migration tests Frontend route tests Offline tests Recovery tests Sync tests Printer failure tests Duplicate submit tests Permission tests Security/privacy tests No-placeholder scan

## 17.3 MVP Acceptance Flow

The MVP is accepted only if this passes:

txt id="pyc2ae" 1. Start POS app. 2. Startup screen checks local health. 3. Login as authorized cached user. 4. Open cashier session. 5. Create draft bill. 6. Select/create patient. 7. Add service. 8. Refresh frontend and confirm draft remains. 9. Restart backend and confirm draft remains. 10. Finalize cash bill. 11. Confirm bill/payment/receipt/sync event/audit log are created. 12. Print receipt. 13. Simulate printer failure and retry. 14. Disable internet/network. 15. Create another cash bill offline. 16. Confirm sync event remains pending. 17. Restore network/server. 18. Confirm sync retries. 19. Simulate crash after draft creation and recover draft. 20. Simulate crash after finalization and recover finalized bill. 21. Double-click finalize and confirm only one bill exists. 22. Close cashier session. 23. View today collection report. 24. View sync status screen. 25. View support/health screen.

## 17.4 Exit Gate

Phase 11 is complete only when:

txt id="n9297m" All P0 acceptance tests pass. No fake UI remains. No broken route remains. No critical API mismatch remains. No duplicate financial action bug remains. Recovery works. Offline billing works. Sync pending/retry works.

# 18. Strict Feature Dependency Map

## 18.1 Draft Billing Depends On

txt id="8uvv8g" Auth Permissions Device identity Cashier session Patient Catalog/services Database migrations Audit foundation

## 18.2 Bill Finalization Depends On

txt id="p29qv9" Draft billing Idempotency Payments Receipts Sync events Audit logs Cashier session

## 18.3 Receipt Printing Depends On

txt id="gcb405" Final bill Receipt record Printer job table Printer adapter Audit logs

## 18.4 Recovery Depends On

txt id="l2cuaq" Runtime state Drafts Sessions Bills Payments Receipts Printer jobs Sync events Recovery markers Audit logs

## 18.5 Sync Depends On

txt id="nfwj6g" Sync events Idempotency Device identity Tenant identity Business records Audit logs Retry rules

## 18.6 Reports Depend On

txt id="mgy76e" Bills Payments Cashier sessions Bill item snapshots Sync events Refunds later Voids later

# 19. What Must Not Be Built Early

Do not build these before MVP core works:

txt id="93civ4" Complex admin dashboard Advanced analytics AI report summary Insurance billing Advanced IP billing Full pharmacy inventory Real gateway settlement Multi-branch SaaS dashboard Remote device fleet management OTA updates Full custom Linux distro

Early overbuilding will create broken modules and slow down core correctness.

# 20. Codex Execution Rules

When using Codex or any coding agent, every prompt must include:

txt id="8cdl3e" Which phase this is Which documents apply Which files may be changed Which files must not be changed Exact required APIs/tables/screens No-placeholder rule Test requirements Acceptance criteria

Codex must not be given vague prompts like:

txt id="vco4dj" Build the POS dashboard. Make the billing module. Create all screens. Add sync. Make it production-ready.

Correct Codex prompt shape:

```txt id=“5oe5b7” You are implementing Phase 4 — Draft Billing.

Use: Document 2 Requirements Document 3 Database Schema Document 4 API Contract Document 5 Screen Map Document 8 Development Rules

Implement only: - bill_drafts - bill_draft_items - create/list/get/update draft APIs - add/edit/remove draft item APIs - frontend draft workspace - tests

Do not implement finalization, payment, receipt, sync worker, reports, or extra modules yet. No placeholder buttons. All buttons must call real API, route to real screen, be disabled with reason, or hidden.

---

# 21. Pull Request Acceptance Rules

Every PR must include:

```txt id="2otbb7"
Phase number
Requirement IDs
Files changed
Database migrations
APIs changed
Screens changed
Tests added
Offline behavior
Recovery behavior
Known limitations
Screenshots if UI changed

A PR must be rejected if:

txt id="xvxwa3" It adds fake buttons. It adds fake data to production route. It changes API contract silently. It changes schema without migration. It lacks tests for P0 behavior. It creates frontend/backend mismatch. It breaks previous phase acceptance gate.

# 22. Phase Completion Sign-Off Template

Each phase must be signed off using this format:

txt id="utk0u9" Phase: Implemented: Documents followed: APIs completed: Tables/migrations completed: Screens completed: Tests passing: Offline behavior: Recovery behavior: Known issues: Decision: Approved to move next phase / Blocked

# 23. First Codex Prompt After Document 9

The first Codex prompt should not build billing.

It should build Phase 0 only.

```txt id=“mrks1r” You are implementing Phase 0 — Project Foundation for the POS Appliance Platform.

Use the locked project documents as source of truth: Document 1 — Architecture Document 4 — API Contract Document 5 — Screen Map Document 8 — Development Rules Document 9 — Implementation Master Plan

Goal: Create the project foundation only.

Implement: 1. Repository structure: - backend/ - frontend/ - shared/ - docs/ - os/ - scripts/

- Backend FastAPI skeleton:

  - app/main.py

  - app/config.py

  - app/core/responses.py

  - app/core/errors.py

  - app/core/logging.py

  - app/core/request_id.py if needed

  - app/health/router.py

  - app/startup/router.py

- Standard API response format: Success: { “success”: true, “data”: {}, “request_id”: “REQ-…” }

- Error: { “success”: false, “error”: { “code”: “ERROR_CODE”, “message”: “Human-readable message.”, “details”: {} }, “request_id”: “REQ-…” }

- Backend endpoints:

  - GET /api/v1/health

  - GET /api/v1/health/version

  - GET /api/v1/startup/status

- Frontend skeleton:

  - central API client

  - /startup route

  - /system/api-unavailable route

  - /system/support-required route

  - /permission-denied route

  - basic app shell

- Frontend startup screen must call:

  - GET /api/v1/startup/status

  - GET /api/v1/health

  - GET /api/v1/health/version

- Environment config:

  - development

  - staging

  - demo

  - production

- Basic tests:

  - backend health endpoint test

  - backend version endpoint test

  - startup status endpoint test

  - frontend startup screen renders

  - frontend API unavailable state renders

Strict rules: - Do not implement billing. - Do not implement login yet. - Do not implement database yet. - Do not add fake dashboard. - Do not add fake buttons. - Do not add placeholder routes. - Do not use fake success messages. - Every visible button must route to a real screen, call a real API, be disabled with visible reason, or be hidden.

Acceptance: Phase 0 is complete only if: - Backend starts. - Frontend starts. - Startup screen shows real health/version/startup response. - API unavailable state works when backend is unavailable. - Standard response and error formats are implemented. - Request ID appears in responses. - No placeholder production button exists.

---

# 24. Implementation Risk Controls

## 24.1 Risk: Codex Builds Too Much

Control:

```txt id="etkj5y"
Give phase-scoped prompts only.
Explicitly say what not to build.
Reject extra unrelated modules.

## 24.2 Risk: Fake UI Appears

Control:

txt id="r8u1rr" Run no-placeholder scan. Inspect every visible button. Require route/API mapping.

## 24.3 Risk: Frontend/Backend Drift

Control:

txt id="2k8mng" Use Document 4 API contract. Generate shared types if possible. Do not rename endpoints casually.

## 24.4 Risk: Database Chaos

Control:

txt id="gcpyt7" Migration-only changes. No manual DB editing. Test fresh and upgrade migrations.

## 24.5 Risk: Broken Billing Flow

Control:

txt id="qtxqti" Do not add extra modules before one full billing flow works. Protect Phase 5 acceptance gate.

# 25. Final Implementation Acceptance Checklist

The implementation plan is accepted only if:

txt id="v68nb2" Build order is clear. Phase boundaries are clear. Codex prompts can be phase-scoped. Backend comes before fake frontend complexity. Database migrations are planned. API contract drives frontend. Recovery and sync are not afterthoughts. No-placeholder rule is enforceable. MVP acceptance gate is clear.

# 26. Document Freeze Statement

This Implementation Master Plan is the execution baseline for the POS Appliance Platform.

Implementation must proceed in controlled phases:

txt id="bw2105" Phase 0 — Project Foundation Phase 1 — Database Foundation Phase 2 — Auth, Device, Permissions, Sessions Phase 3 — Master Data, Patient, Catalog Phase 4 — Draft Billing and Autosave Phase 5 — Bill Finalization, Cash Payment, Receipt, Outbox Phase 6 — Receipt Printing and Printer Jobs Phase 7 — Recovery Engine Phase 8 — Sync Engine Phase 9 — Reports, Settings, Health, Support Phase 10 — OS/Kiosk Packaging Foundation Phase 11 — MVP Hardening and Acceptance Testing

No development phase should begin until the previous phase passes its exit gate.